## Rampup Plan
Phase | Phase Objective | Detail | Expected Outcome | Reference | Mentor | Duration (Man-day) | From Date | To Date
Phase 1 | Project Overview + Environment Setup | PRM project overview | To have basic understand about PRM Project | Figma design: https://www.figma.com/file/l01TZwrYdrdLaXYG0XtMF7/PanL-Room-Manager?node-id=338%3A2731 Project folder structure: \\brtsgfs1\Data\General\Projects\SoftwareEngineering\PanL | Tiep | 2 | 2022-10-11 | 2022-10-12
|  | PDM project overview | To have basic understand about PDM Project | https://brtchip.atlassian.net/wiki/spaces/PDM/pages/249593927/VER+team+s+Ramp-Up+on+PDM | Lam | 2 | 2022-10-13 | 2022-10-14
|  | SW Process | To have understanding about SW Process in BRT |  | Hien | 1 | 2022-10-10 | 2022-10-10
|  | Environment Setup | Working environment - Request admin permission from IT - Setup necessary tools (Virtualbox, Editor/IDE, DB clients …) | Permission request link: https://forms.office.com/Pages/ResponsePage.aspx?id=mCC7oiJqfUGxllWsMpvdFxFJiYH9CL9HptSo6BWOR3xURFhURlNTVTNEMFE1TldaUEtONlg3S0pBSi4u | Nghi | 5 | 2022-10-10 | 2022-10-14
|  | Angular ramp up | - Gain enough angular skill for working with WMC: 1. Data-binding 2. Scope 3. Controller 4. Service 5. Filter 6. Directive 7. Template 8. Routing 9. MVC/MVVM 10. Dependency Injection |  | Nghi | 7 | 2022-10-17 | 2022-10-25
|  | Project structure and code walk through PRM WMC | - Familiar to source code structure |  | Tiep | 3 | 2022-10-26 | 2022-10-28
|  | Project structure and code walk through PDM WMC | - Familiar to source code structure |  | Abhijith | 3 | 2022-10-31 | 2022-11-02
Phase 2 | Project Hands on | Deploy PRM + Basic configure + Booking | - Able to deploy - Basic usage understanding |  | Tiep | 2 | 2022-11-03 | 2022-11-04
|  | Deploy PDM + Basic configure + Booking | - Able to deploy - Basic usage understanding |  | Tiep | 2 | 2022-11-07 | 2022-11-08
|  | Fix PRM WMC bug | - Able to identify the cause and fix the issue |  | Tiep | 10 | 2022-11-09 | 2022-11-22
|  | Fix PDM WMC bug | - Able to identify the cause and fix the issue |  | Abhijith | 10 | 2022-11-23 | 2022-12-06
Phase 3 | PRM/PDM integration overview | Introduce to solutions of integrations | To have basic idea on how PDM/PRM will be integration | https://brtchip.atlassian.net/wiki/spaces/PRM/pages/642088972/PRM+PDM+Integration+-+DRAFT | Nghi | 3 | 2022-12-07 | 2022-12-09
50